## High level plan
# | Task Name | Task Description | Duration (days) | Estimation remark | due date | Owner | Predecessors | Status | Risk | Risk mitigation
1 | HLD + Review | Write HLD for Client and Server solution that present live tree of devices connected via USB to a device | 2 | Client - 1-2 days Server 2 days |  | Product owner
2 | Client LLD and development | Technical Document describing client functionality including screen mockup , develop react side, write CSS etc and UT | 5 |  |  | client/UI expert
3 | Server LLD and development | Technical document describing server business logic, configuration, integration and data objects involved. Develop service ,data,api and third pary services calls (implement webserver like Apache, NGNIX, Other) and UT | 7 |  |  | Server expert
16 | QA | System,integration,Performance and security testing | 4 | assuming minimum browser requirements are set (e.g. should not work with Internet Explorer 4...), and Servers have also min spec |  | tester
20 | packaging + deployment 1+2 days (like an installer, but just for nodejs) | Document that describe how & what to deply to have the SW package working | 1 | write installer for nodejs |  | Infra
24 | Production bug fixing | Fix bugs if any | 2

## Technical debt tasks
ID | Name | TD category | Task description | Priority | responsible
2 | fix architecture | Architecture Debt | align server/service layer/data layer architrcure , CDN for better availability/Performance ? , | Hige | SW architect
3 | Fix bugs | Code Debt | fix device name (currently due to USB drivers cant display the device name in tree) | Urgent | Developer/expert
4 | User expiriance and Usability | Design Debt | align to product look and feel, update CSS file | Medium | UI expert
5 | integration test | Test Debt | Check integration with other devices/hardware components/OS like Mac , ios, android etc , Different web bwusers | High | Tester
6 | system test | Test Debt | Perform E2E testing including regression | High | tester/ST
7 | performance | Code Debt | change code/architecture to support the requiered number of users/all supported HW/no of threads | High | expert
8 | Align documentation | Documentation Debt | write documentaion (HL/LV) | High | Product owner
9 | Add security | Code Debt | 1. add Security (ability to login, get user/PWD) 2. pass user creditential from client to server | Urgent | Developer/expert
10 | Security testing | Test Debt | test for security break (static & | Urgent | tester
11 | User Management | Environmental Debt | define users/permissions | High | Developer/expert
12 | Code review | Code Debt | code review by expert | High | Scrum master/expert
13 | Automation | Test Debt | testing automation | High | Developer/expert
14 | Error handling | Code Debt | error handling | Medium | developer
15 | Maintainability | Code Debt | log , Code remarks , naming convention to files/classes etc. | High | developer
16 | Backward compatability | Test Debt | test with all existing product versions to make sure competability is not break and upgrade can done without any impact | High | tester
17
18
19

## Activity-tasks map list
# | Task Name | Task Description | Duration (days) | Estimation remark | due date | Owner | Predecessors | Status | Risk | Risk mitigation
1 | HLD | Write HLD for Client and Server solution that present live tree of devices connected via USB to a device |  |  |  | Product owner
2 | Client LLD | Technical Document describing client functionality including screen mockup |  |  |  | Scrumteam/Master with UI expert
3 | Server LLD | Technical document describing server business logic, configuration, integration and data objects involved
4 | Service Layer | Apply business logic - write the business logic which USB is parent/hub who is leaf)
5 | Data access layer | Accsess security data , get the Vendor , Product Ids , name , type and connection status from USB service)
6 | API routes
7 | Controller
8 | layer for third-party services calls | Class that call System USB package and get info to array/Jason
9 | Server unit testing | Perform unit test for the server side
10 | Client - APP | presentation of live tree of the devices connected via USB to the server's machine.
11 | tree-graph | Write Tree Graph object (HTML/SVG) or use OOB react- tree-graph
12 | CSS -StyleSheet | CSS Design
13 | Fetch USB details | Fetch Vendor and Product Ids , name , type and connection status
14 | presentation/Screen | present the tree in a way that a USB hub is a branch, and a device is a leaf. For each leaf/branch present: Vendor and Product Ids , name , type and connection status
15 | Client unit testing | Test the client (Look and feel, page is loaded, error handling)
16 | Integration
17 | Client Server commonication | Send data to client when react is ready every 4 second via HTTP transport. Code should be flexable/maintainable to change quickly to any protocol like TCP "e.g. by using WebSockets"
18 | Security manager | Login - user PSW screen to get user info
19 | Integration test | Client Server integration , Security integration
20 | Release note | Document that describe how & what to deply to have the SW package working
21 | System test | perform system testing/versioning/product backward competability etc..
22 | UAT | Support customer testing and bug fixing
23 | Production Deployment | Deploy SW in production enviroment
24 | Production bug fixing | Fix bugs if any
Deliverable
A zip file that includes the project's code. Operating the solution should be done with a minimal
setup, and described in a README file within the project.

## TD category
Category | Category Description
Code Debt | Poorly written code that can be found as a problem in the source code, requires refactoring and violates best programming practices or programming rules. Examples of code debt are code duplication, over-complex code, bad style that reduces readability, and poorly organized logic
Design Debt | Violations and shortcuts in the principles of good design that underfocus on qualities such as maintainability and adaptability
Architecture Debt | Sub-optimal solutions and bad decisions in software architecture, which compromise internal quality aspects, such as maintainability, performance, robustness, modularity etc. In addition, architecture debt can be a solution that becomes sub-optimal when technologies
Environmental Debt | Debt that happens in the environment of the application, which can include development, hardware, infrastructure, and supportingrelated challenges; for example, manual processes that could be automated to increase productivity, or postponement of upgrades to infrastructures and components.
Documentation Debt | Missing, inadequate, insufficient, incomplete, or outdated documentation found in any aspect of software development.
Test Debt | Shortcuts in testing such as lack of unit tests, integration tests, acceptance tests, written test scripts, code coverage, or the number of test cases being completed.
Requirements Debt | The distance between optimal requirements specification and actual system implementation, for example, requirements that are only partially implemented.
Build Debt | Flaws in a software system built process, which makes it overly complex, time consuming, unnecessarily slow, and difficult.
Infrastructure Debt | Sub-optimal configuration of development-related processes, activities, technologies, supporting tools etc. Delays upgrades and infrastructure fixes, which have an effect on team productivity.
Defect Debt | Defects, bugs, or failures found in software, which are often identified by testing activities or bug tracking systems.
Test Automation Debt | Lack of work involved in automating tests to support continuous integration and faster development cycles.